## Sheet1
Toward a comprehensive Emergency and Preparedness Response Plan in Gaza Strip and the continuation of psychological emergency support in East Jerusalem in the context of increasing occupation related violence
| 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
Result 1 | 2019-04-01: Developed in 12 months the Health Component for 32 Governmental Designated Emergency Shelters (DES) in Gaza Strip.
R1 A1 : Digital mapping of Des | bar: 2019-04-01 to 2019-05-01
R1 A2 : Medical need assessment | bar: 2019-04-01 to 2019-06-01
R1 A3: Rehabilitation of spaces in Shelters | bar: 2019-07-01 to 2019-12-01
R1 A4 : Coordination with others cluster | bar: 2019-04-01 to 2020-03-01
R1 A5: Presentation of DES EPREP to key actors and stakeholders (MoH, MoE, WHO, OCHA, HNC) | bar: 2019-09-01
Result 2 | 2019-04-01: Developed CP for 15 PHCC in charge of ensuring lifesaving interventions and medical services to IDPs in DES and out DES in the context of the EPREP in Gaza.
R2 A1 : workshops with MOH and PHD and PHC directorate | bar: 2019-04-01; 2019-06-01
R2 A2 : workshops with PHC | bar: 2019-05-01; 2019-07-01
R2 A3 : production of the CP at PHC | bar: 2019-08-01 to 2019-09-01
R2 A4 : procurment of preposition medical stock | bar: 2019-10-01 to 2020-02-01
R2 A5 and R3. A6: Drills ( 1 day) | bar: 2020-01-01 to 2020-02-01
Result 3 | 2019-04-01: Medical staff in charge of providing lifesaving attention and quality cares to IDPs in-DES and out-DES, as part of EPREP in Gaza, trained and capacitated.
R3 A1 : PHTLS training and certification for emergency doctors and energency nurses belonging to selected PHCC. | bar: 2019-07-01 to 2019-12-01
R3 A2: Refreshment training in the management of more prevalent problems for most vulnerable groups. | bar: 2019-07-01 to 2019-12-01
R3 A3 : Training in MH Gap. | bar: 2019-07-01 to 2019-12-01
R3 A4: Training in EWS on epidemics and basic health information systems. | bar: 2019-07-01 to 2019-12-01
R3 A5: Training in identification and medical management of SGBV survivors. | bar: 2019-07-01 to 2019-12-01
R3 A6: 1 drill per year for every PHCC to test implementation of CP (simulation plus feedback workshop) | bar: 2020-01-01 to 2020-02-01
Result 4 | 2019-04-01: Strengthened community response capacity and resilience (both displaced and host communities), within Gaza EPREP framework
R4 A1: Election of community health first responders (CHFR) (among both potential displaced and host communities) | bar: 2019-04-01 to 2019-05-01
R4 A2: BLS-AED training and certification for CHFR. | bar: 2019-06-01 to 2019-11-01
R4 A3: Psychological First Aid (PFA)and Psychoeducation training for CHFR. | bar: 2019-06-01 to 2019-11-01
R4 A4: Training on community epidemiological triggers monitoring for CHFR. | bar: 2019-06-01 to 2019-11-01
R4 A5: Capacitation on referral pathway between DES, PHCC and community. | bar: 2019-06-01 to 2019-11-01
R4 A6: Participation of CHFR in drills of PHCC within their area of responsibility. | bar: 2020-01-01 to 2020-02-01
R4 A7: Dissemination of EPREP key messages through IEC tools. | bar: 2019-12-01 to 2020-03-01
Result 5 | 2019-04-01: Strengthened resilience for communities in East Jerusalem living under occupation and affected by settlers' violence, demolitions, forced displacement and abusive use of force by ISF.
R5 A1: Provision of MHPSS support including emergency/first aid interventions to persons/communities affected by occupation-related critical events. | bar: 2019-04-01 to 2020-03-01
R5 A2: Identification, referral and follow-up of cases in need of urgent protection, in coordination with protection Consortium and cluster. | bar: 2019-04-01 to 2020-03-01
R5 A3: Identification, treatment, referral and follow-up of cases in need of urgent specialized MH services. | bar: 2019-04-01 to 2020-03-01
R5 A4 : Psychoeducation sessions for most vulnerable groups and communities. | bar: 2019-04-01 to 2019-05-01; 2019-07-01 to 2020-03-01
Result 6 | 2019-04-01: Improved the awareness of general public upon the impact of occupation-related violence on the mental health of population living in West Bank.
R6 A1: Conduct a study upon the impact on mental health caused by occupation-related violence in West Bank | bar: 2019-07-01 to 2019-09-01
R6 A2: Produce, print and publish the results of the study. | bar: 2019-10-01
R6 A3: Dissemination of results among key stakeholders. | bar: 2019-11-01; 2020-01-01 to 2020-03-01